## Product Launch - Mar 2025 and l
PM | Capability | Target Release month | Outcome | Execution Notes | Engineering Team | Design | PRD | Figma Link | Marketing lead | Workflow deck | rbac dependency | Doc Owners | Doc Link | Engineer | Marketing PR Linear link
August release
Dharani | Inmobi - Bulk import of TF modules to AppStack | Aug | Script to Inmobi 7/25 commit; productize it by end of Aug |  | Arch |  | [Aug-PRD] - Bulk import custom modules as different AppStacks | CLI only MVP; TBD - tradeoff visual topology vs security scan flow |  | https://linear.app/stackgen/issue/PRO-98/enhancement-inmobi-enhancement-service-account-field-format-limitation
Dharani | MSCI - provider version enforcement for governance config | Aug | MSCI: Needed for provider version update every quarter |  | Platform |  | [Aug-PRD] StackGen Governance Enforcement for Terraform Versions, Provider Versions, and Unit Test Execution | https://www.figma.com/proto/tRmahr3URh4eotmgIEsQN8/TFtest--Terraform--tf----Provider-Version-Enforcement?page-id=0%3A1&node-id=5-8345&p=f&t=AuIaBKa73NGsoEEW-1&scaling=scale-down-width&content-scaling=fixed&starting-point-node-id=5%3A8345&show-proto-sidebar=1
Dharani | MSCI - StackGen deploy / tf test command local TF code runs with AppStack ID context | Aug | MSCI: Needed for Atlantis local runner support |  | Platform |  | [Aug-PRD] StackGen Governance Enforcement for Terraform Versions, Provider Versions, and Unit Test Execution | https://www.figma.com/proto/tRmahr3URh4eotmgIEsQN8/TFtest--Terraform--tf----Provider-Version-Enforcement?page-id=78%3A13463&node-id=78-13464&t=jBYbfKt0nkbNfTzF-1&scaling=min-zoom&content-scaling=fixed&starting-point-node-id=78%3A13464&show-proto-sidebar=1
Dharani | Discovery Agent | Aug | Customers can find resources and subset of resources within Appstacks - Search engine |  | Cloud |  | [Aug-PRD] - Cloud discovery agent | https://www.figma.com/proto/v0XiLQ96vK3W9F4qH1tHEX/Agentic-AI-DX?page-id=1642%3A90530&node-id=1642-91034&p=f&viewport=312%2C443%2C0.06&t=4KIy2StawvZ2hpgb-1&scaling=min-zoom&content-scaling=fixed&starting-point-node-id=1642%3A91034 | alex@stackgen.com
Dharani | StackBuilder Hardening | Aug | Fix bugs in StackBuilder |  | DPP |  | N/a
Aaron | Aiden Integration | Aug | Integration of Aiden with StackGen functions |  | DPP |  | OpsVerse & Stackgen Integration
Aaron | API calling in Aiden | Aug |  |  | DPP |  | [PRD] REST API calling in Aiden | TBD
Aaron | StackBuilder using Modules | Aug | IaC and appStack generation to prioritize using pre-built modules in the catalog |  | DPP |  | [PRD] StackBuilder Using Modules
Aaron | StackGen Expert in Aiden (integration) | Aug | Connect Aiden to StackGen capabilities via APIs or MCP server |  | DPP
Dharani | Governance policy editor Agent | Aug | Create custom policy using natural language |  | Cloud |  | [Aug-PRD] StackGen Rego Policy Generation & Enforcement from Natural Language using an AI Agent | https://www.figma.com/proto/5ZuQlGzTzpuEJfS4CPDLg1/%F0%9F%9B%A0%EF%B8%8F-OPA-Rego-Custom-Policy-Management?page-id=78%3A2991&node-id=110-15866&p=f&viewport=249%2C496%2C0.05&t=3gN2egBgPrOCNFJt-1&scaling=min-zoom&content-scaling=fixed&starting-point-node-id=110%3A15866
Dharani | Rego policy support with OPA engine | Aug | customers can import policies maintained in Wiz, checkov |  | Cloud (This will be started but not completed in August) |  | [Aug-PRD] StackGen OPA Policy Import: Enterprise Rego Policies from Wiz and In-House Repos
Dharani | Drift Analyzer Agent | Aug | Developers can analyze cost and compliance escalations using drift. Also, platform eng can review top drifting resources and user principal creating drift |  | DPP |  | [Aug-PRD]-Drift Analysis Agent | https://www.figma.com/proto/v0XiLQ96vK3W9F4qH1tHEX/Agentic-AI-DX?page-id=1232%3A42424&node-id=1268-13014&viewport=236%2C447%2C0.04&t=GDsX7bW8VHNDpjmi-1&scaling=min-zoom&content-scaling=fixed&starting-point-node-id=1268%3A13014 | alex@stackgen.com
Below stories punted
Aaron | Learning Agent - StackScribe | Aug | First cut of learning agent for (drift + provision) and knowledge graph |  | DPP |  | [PRD] StackScribe - Learning Agent
Aaron | Deployment Agent | Aug | Deployment of IaC into AWS through ArgoCD pipelines |  | DPP |  | [PRD] Deployment Agent v0
Aaron | LLM API Gateway - AI Control Plane | Aug | LLM API Gateway enables us to add LLM model routing, improve LLM observability, and implement real-time security and compliance checks |  | DPP |  | [PRD] LLM API Gateway
Aaron | Multi agent workflow / command center | Aug |  |  | DPP |  |  | multi-agent figma flow
Dharani | Cross account resource Visibility - Conde Neste ask | Aug | Resource list view support multiple tftstate, accounts for cloud scan |  | None for this month. We need more clarity on this one.
Dharani | Developer Day 0 agent with Backstage | Aug | Reverse flow write to backstage - Spacelift parity |  | Arch |  | [Aug-PRD]-Developer onboarding using Backstage catalog & templates | Figma: Backstage agent 4 usecases | alex@stackgen.com
July release
Dharani | Developer Day 0 agent only Git | 2025-07-22 | eng release by July 22nd; Use for july 22nd marketing campaign; Demo version 1 handoff by eng to PM/PMM on July 16th; Demo version 2 to PM/PMM on July 18th |  | Thursday eng demo to Marketing; |  | [PRD-July] Prompts for developer assistance Agent | For Eng - Use case 1 - Figma mockups; For Marketing - https://www.figma.com/proto/v0XiLQ96vK3W9F4qH1tHEX/Agentic-AI-DX?page-id=714%3A40827&node-id=714-44869&p=f&viewport=-1223%2C671%2C0.08&t=hgF8XOxdLs29eGdx-1&scaling=min-zoom&content-scaling=fixed&starting-point-node-id=714%3A44869 single flow: https://www.figma.com/proto/v0XiLQ96vK3W9F4qH1tHEX/Agentic-AI-DX?page-id=1372%3A35586&node-id=1372-39047&p=f&viewport=376%2C467%2C0.02&t=5R0TOibyCe5tr1it-1&scaling=min-zoom&content-scaling=fixed&starting-point-node-id=1372%3A39628 | alex@stackgen.com
Dharani | TF module editor coding agent | Release on July 8 publicly | Use product for screenshots |  |  |  | [PRD-June]-Module Editor public release |  | alex@stackgen.com
Ban Columbia PHASE 1 / Inmobi asks
Dharani | Azure Devops support | July | push generated iac to azure devops |  | platform |  |  | Figma: Push to Azure DevOps
Dharani | Cloud to code TFstate carve out (phase 2 - state mgmt in smaller appstack) | July | Existing feature launched early June. Release notes here. |  | cloud |  |  | NA
Dharani | AppStack set (phase 1 - support Appstack set deploy over CLI with drift remediation on underlying AppStack) | July | Deploy appstack B which depends on appstack A; If Appstack A has drift, then remediate drift on Appstack A before deploying Appstack B; Two options to user: Option 1 - Automatically remediate drift and deploy appstack B; Option 2 - Ask user ever time a new deployment happens. MVP will be CLI for deployment; Provide a system wide setting for automatic drift remediation on underlying appstack. MVP for UI will be listing AppStack sets. Creation of appset will be CLI |  | cloud |  |  | A rough concept to visulize appStack Set (Note: this needs discussion with larger group)
Dharani | Webhook notifications for AppStack creation, AppStack new version creation, policy creation. Drift & notification | July | Already in progress based on Travelodge feedback/need. PRD here now includes a future work section for end of July scope |  | workflow
Dharani | Project settings & Integrations | July | Leverage existing flow for release. Show mockups for marketing |  |  |  |  | Figma: Jira Integration; Figma: Project Settings; Activity Log: https://www.figma.com/proto/v0XiLQ96vK3W9F4qH1tHEX/Agentic-AI-DX?page-id=0%3A1&node-id=21-16913&p=f&viewport=391%2C266%2C0.04&t=aYCsKi7Pnpuefb0Q-1&scaling=scale-down-width&content-scaling=fixed&starting-point-node-id=21%3A16913&show-proto-sidebar=1 | alex@stackgen.com
- UX cleanup to configure git repo without any resource added to appStack - Hide Repo Column and make it Output repo to configure IaC repo
Dharani | Cursor plugin for TF module editor with compliance best practice enforcement | July |  |  | arch
Aaron | AI control plane improvements | 2025-07-22 | Enable first agents for StackGen Core such as IaC agent, Deployment Agent, etc |  | DPP |  | https://docs.google.com/document/d/1jEsfhznchyCxRQK_NP9AMmueiRo7X02DO5JjEVbtZe4/edit?tab=t.0 |  | alex@stackgen.com
Aaron | AI control plane improvements | 2025-07-22 | Enable first agents for StackGen Core such as IaC agent, Deployment Agent, etc |  | DPP |  | https://docs.google.com/document/d/1jEsfhznchyCxRQK_NP9AMmueiRo7X02DO5JjEVbtZe4/edit?tab=t.0 |  | alex@stackgen.com
Cut line
Ban Columbia PHASE 2
| JFrog Artifactory support | August | credential to jfrog; |  | arch |  |  | Figma: Intgerationwith jFrog Artifcatory
| Cloud to code TFstate carve out (phase 3 improvements - Keep track of resources in smaller appstack) | August | Existing feature launched early June. Release notes here. |  | cloud |  |  | NA
| AppStack set (phase 2 - Make variable sharing easier to use for dependent module) | August
| Cloud to code TFstate carve out (phase 2 - remember resources already added in previous carveout) | August
| Custom module version enforcement in each AppStack (Phase 2: Detection) | August
| Custom module force upgrade to later version of AppStack (phase 3: Remediation) | September
| Module editor save to generate a PR instead of only saving locally | august
| Security scanning for custom modules | June | import from TF registry, publish to stackgen catalog, run stackgen scanner, remediate scan results using module editor, publish the hardened module back to catalog, now reference the hardened module within AppStack. Customer should be able to write governance rule that imported custom modules should have scanning complete | Sean/Suvarna | Platform |  | [PRD-June] Custom TF module security scanning | Flow 1 - Security Status column in Module Catalog Flow 2 - Fixing module with Catalog
| Add support for OPA (Rego policies) by extending our custom policy support (a ka BYO policies) | June | copy paste policy, git import, wiz, and then gen ai | Suvarna | Cloud |  |  | Create Custom Policy
| folder restructuring within module editor |  | [innovaccer] | Suvarna | Cloud
| Drift notification & Azure monitor/cloudtrail integration | June | webhook for splunk/slack/email; | Nasir | Workflow |  | [PRD-June] - Drift external & inbound integrations | Flow 1: Drift Remediation Flow 2: Drift Alerts
| community project - image to IQ | June | start with diagram & provide iac & well-architected opinion using chat interface. Reference use case here | Jigar | Workflow |  |  | Flow 1: Desktop Flow 2: Mobile
| TF module editor public launch | June | Target power users who want to update Terraform modules for region expansion, security, or compliance needs. MVP: Customer enters into module editor with intent to create, publish module custom modules. Create a single tf module file within module editor thru' copy/paste, tf registry or git repo. Publish module to catalog and perform StackGen provided security scanning. Activity log for create, scan, and publish. New module version gets created on publish. MVP+1: Make a copy of tf module from a visually created Appstack from scratch (greenfield); Appstack created from cloud to code (brownfield); Resource pack created from Appstack; MVP+1: Push to git; overwrite existing module file on stackgen during an ingest from git | Kunal | Arch |  | https://docs.google.com/document/d/1dTfngxIY4EwnPYg1JWevAf_9RlTotFX50WTwT9GOAaE/edit?tab=t.0#heading=h.t1xyiiiegnj2 | Flow 1 (MVP): Module editor to AppStack Flow 1 (MVP): Activity Logs for Module Managment Flow 2 (MVP+1): AppStack to Module editor (to be updated)
| Backstage reverse flow | June | Generate Backstage system model YAMLs from appStacks
| version enforcement of modules | June |  | Kunal | Arch
| MCP server | June | Expose self-servicing and Visibility (activity logs) API endpoint as MCP servers. Enable external agents for infra creation & security analysis
| LLM Gateway | June |  |  | DPP
| StackHealer MVP | June/July |  |  | DPP |  |  | Flow 1: K8s related incident Flow 2: Terraform related incident Setting: Level of Autonomy |  |  |  | Aaron
| Document public apis for self serve, Activity log | June |  |  | Documentation
| platform con mockup | June |  |  | Product
End of May summary release narrative
| StackGen CLI wrapper for TF commands | May | customers can run CLI thru' Github actions and provide CLI run status within StackGen dashboard | Initial version by May 12 with Bank of col only; | Workflow |  | [PRD-May-Release] StackGen TF command line for CI/CD integration | CI Runs Types and its dashboard under CLI View Crosslaunch from appStack to CLI Runs |  |  |  | Saumya
| CLI runs for Audit Logging | May |  | Initial version by May 12 with Bank of col only; focus on TF init/plan/apply/destroy | Workflow |  | Same as above | Same as above |  |  |  | Saumya
| Compliance dashboard enhancement | May | Provide control ids - Innovacer ask |  | Cloud | https://linear.app/stackgen/team/CLOUD/projects/view/may-release-4e8ae05d75e5 | [PRD-May-Release] StackGen Compliance Dashboard | compliance dashboard figma Alternative approach of crosslaunch Compliance Dashboard, Crossluanch 1, Crosslaunch 2, Crosslaunch 3 |  |  |  | Saumya
| Sales engineering PoC APIs | May | Create AppStack, create resource type, create topology, create tfvar config
| RBAC - Active directory sync | May | Rename teams to projects in UI/docs. Active directory support for projects |  | Platform |  | [PRD-May-Release] StackGen RBAC teams expansion |  |  |  |  | Talk to Sean
| Stackgen for Stackgen - Greenfield & Brownfield | May | Greenfield: Build a reliable & compliant cloud to our customers built using Stackgen. Brownfield: Cloud Discovery for governance & cost use cases |  | Platform |  |  | NA
| Nested modules | May | MVP: multiple tfstate import; nested module based on tf code folder structure; MVP+1: stack deployment (june) |  | Cloud |  |  | Figma For Multiple tfstate and nested modules |  |  |  | Sid
| Module lifecycle management - version enforcement | May |  |  | Platform
| TF editor | May | able to cross-launch or side-by-side editor from canvas. Being able to seamlessly move from canvas to editor; genai for iam rego policy |  | Arch |  | [PRD-May-Release] TF module editor with canvas experience | Canvas + Module editor experience 1(inline edit) Policy editor + AI |  |  |  | Sid
| Backstage reverse flow pilot | May |  | figma first in May 12; Prototype by TBD | Arch | [6 empty] | Vardhaman/Bhavya
| usability workshop (validate stackgen core workflows with example applications) | May | fix bugs |  | ?
| StackGen Unified MCP Service | May |  |  | DPP
| LLM Gateway | June |  |  | DPP
| StackHealer MVP | June/July |  |  | DPP | [6 empty] | Aaron
| Add support for OPA (Rego policies) by extending our custom policy support (a ka BYO policies) — alpha quality | June |  | push right to june (capacity) | Cloud & Platform
| security scanning for custom modules (stretch) | June |  | push right to june | Platform
Drag and drop - throwing errors on canvas (delays), helm not populating,
| Additional resource support - Azure | Apr | Azure destination - Must have's based on version 1, metanet, nba |  |  | Sagar Sutar
| Topology viewer improvements for large resource count | Apr | Topology view for small resource count. Tabular view for larger count | May 6th |  |  | [PRD-April-Release] StackGen Infra Composer - Large resource count support | - Tabular view tab inside the appStack - Creating appStack from discovered resources (same as above requirement) - Grouping of resources imported within a state file into their originzated modules if those modules have been added into StackGen. - GenAI-driven recommendations for unsupported resources
| Revised UX Flows to decouple visualizer, cloud 2 code, code 2 cloud | Apr | Decoupled entry flows for AppStack Visualizer, Modernization using cloud to code, Migration using code to cloud - Public GA Launch | May 6th |  | Sagar Sutar | [PRD-April-Release]: StackGen Catalog [PRD-April-Release]: StackGen Marketplace
| Custom module workflow enhancements | Apr | Customers like Inmobi plan to use StackGen to enforce / lock down cloud resources used by developers for deployment. Need version level enforcement for developer roles as new modules are published by devops. | May 6th |  | Sagar Sutar |  | - Single and multiple team(s), and enterprise scope for custom module - Enhanced custom module UI for Dev persona - Support for applying different governance config versions to different teams, or change the governance config version for a team - new appStack creation with new gov. config. version - appStack Version creation with new gov. config. version - Gov. UI enhancement - Module Editor UI
| Folder structure improvements for generated modules to fit with ci/cd pipeline | Apr | Inmobi requirement to meet ci/cd environment. Terragrunt community use case | May 6th |  | sagar@stackgen.com
| Gen AI Engine | Apr | - Backend AI engine APIs - SDK/library for both front-end and backend components - Protocols so that AI agents can leverage existing StackGen capabilities (e.g. MCP?) | New target June; Add broken down milestones |  | Sachin | Yes | High |  | N/A | N/A
paper cuts: marketplace to accomodate inmobi, innovacer, nba asks
| Additional Resource support | Mar | AWS destination - initial priority using AutoDesk deployment | https://linear.app/stackgen/project/[customer-support]-aws-primarily-0da1035e69c8/overview | Cloud - Dhairya | None |  |  |  |  | no | Saumya
| Cloud2Code Discovery UI | Mar | Public beta launch available to all customers | https://linear.app/stackgen/project/[cloud2code]-user-interface-8e3ba33baf5b/overview | Cloud | Sagar Sutar |  | https://www.figma.com/proto/naas029a476rDqH4a5l7SP/%5BUX-424%5D-Cloud2Code-Resource-Discovery-UI?page-id=0%3A1&node-id=35-15154&viewport=289%2C349%2C0.03&t=6xRUN2dqw0fh7mWI-1&scaling=scale-down&content-scaling=fixed&starting-point-node-id=35%3A15154&show-proto-sidebar=1 |  |  | no in march - only for devops, custom roles intersection in future | Saumya |  | jigar@stackgen.com
| BackStage integration | CarryOver from Feb | PM to demo customers the POC & refine rqmnts - Autodesk + one customer. No UX update or public launch or press release yet | https://linear.app/stackgen/project/backstage-integration-support-c20e5389b4a9/overview | Architecture & Experience | None | [7 empty] | abhishes@stackgen.com
|  | Mar | Public beta launch available to all customers | https://linear.app/stackgen/project/iac-lm-drift-detection-and-management-ce41cb1527eb/overview | Workflow | Sagar Sutar |  | https://www.figma.com/proto/naas029a476rDqH4a5l7SP/%5BUX-424%5D-Cloud2Code-Resource-Discovery-UI?page-id=0%3A1&node-id=35-15154&viewport=289%2C349%2C0.03&t=6xRUN2dqw0fh7mWI-1&scaling=scale-down&content-scaling=fixed&starting-point-node-id=35%3A15154&show-proto-sidebar=1 |  | StackGen Workflows | only for devops - no dep in march | Saumya |  | nasir@stackgen.com
| TF module editor | Mar | Stackgen dev will use it. We can launch with feature flag as a beta. Customer reaches out to support@stackgen.com | https://linear.app/stackgen/project/terraform-module-editor-7a5986b4b1f8/overview | Architecture & Experience | Sagar Sutar |  | https://www.figma.com/proto/lEO1ESkis1tEMRkPtkReZo/AE-582%3A-Module-Editor-UX?page-id=0%3A1&node-id=153-6314&viewport=226%2C-836%2C0.1&t=VRjwhoAS2FewFgVB-1&scaling=scale-down&content-scaling=fixed&starting-point-node-id=153%3A6314 |  |  |  | Sid | https://docs.google.com/document/d/1WOITW-uxFzR98zqY-JeknQ423MalJ7ZTJWd5_bLuxY0/edit?usp=sharing | shubham@stackgen.com
| RBAC for Devops - TF modules, discovery, and AppStack | Mar | Public launch available to all customers | https://linear.app/stackgen/project/rbac-for-devops-87564e6ef641/overview | Platform | None | [5 empty] | Sid |  | sean@stackgen.com

## Design partnership
Capability | Feedback ask from StackGen | Customer
Infra composer
IaC Gen | usability with common apps
dev ex |  | Docusign, Bancolombia, Siemens, Autodesk
ILM | discovery & drift, backstage | talkdesk, ancestry
governance enforcement
Compliance dashboard |  | Innovacer
Module editor |  | AutoDesk, Inmobi
devex -- Docusign, Bancolombia, Siemens, Autodesk
compliance dashboard -- innovaccer
module editor -- autodesk, inmobi
ILM - talkdesk, ancestry
Arunav Sarkar
IaC gen -- talkdesk, SAP, siemens, autodesk

## PM-Backlog-Asif-Aaron-Dharani-i
| scope | Requesting PM
StackGen deployment log analytics using observenow - cross launch experience |  | Dharani
StackGen AI based rego policy editor within platform eng studio |  | Dharani
StackGen deployment manager tile within Aiden |  | Dharani
Brownfiled custom module import cli - AWS, Azure, and GCP support |  | Dharani
New out of box provider support - Kubernetes, Databricks |  | Dharani
Any feature requests from Innovacer, Autodesk, InMobi, NBA and Nielsen. | compliance dashboard, timeout bug for nielsen, iam policy for nba
StackGen for StackGen use cases—a) Cloud2Code and TF state file to code from existing StackGen deployments in AWS, Azure and GCP, b) validate the generated IaC against the same existing StackGen deployment, c) deploy the generated IaC in a new environment to create a fully functional StackGen platform, d) the greenfield use case of creating the entire set of deployment files for the StackGen platform using the InfraComposer. | EU region expansion
appStack of appStacks | multiple tfstate imports
Finish the support for carving out multiple appStacks from the list of discovered resources from a) cloud account or b) TF state files from the same account (we will have to add the support for importing multiple TF state files in a single shot and also adding resources from additional TF state files to existing list of ‘discovered’ resources.
Finish prompt-based TF generation and editing support for the Module Editor
Custom module support in resource restriction policies
Add versioning support for custom module related enforcements wherever custom modules are supported in custom policies
Add support for OPA (Rego policies) by extending our custom policy support (a ka BYO policies) — alpha quality
Platform robustness and reliability enhancements
Add support for scanning the created (using the Module Editor) or imported TF module using an OSS Tf scanner by default and a BYO scanner
Implement the module publisher’s UI flow (that we have created the mockups for).
Externalized full-fledged versioning for appStacks (at least a complete design)
Module recognition and module-related IaC folder structure in the generated IaC for the reverse (Cloud2Code) flow
support for a post-IaC-generation step for users to BYO scripts for the generated IaC folder reorg, before the generated IaC is pushed to Git.
Feed iac into Backstage as a system model
Ban Columbia PHASE 2
JFrog Artifactory support |  | credential to jfrog; | arch
Cloud to code TFstate carve out (phase 3 improvements - Keep track of resources in smaller appstack) |  | Existing feature launched early June. Release notes here. | cloud
AppStack set (phase 2 - Make variable sharing easier to use for dependent module)
Cloud to code TFstate carve out (phase 2 - remember resources already added in previous carveout)
Custom module version enforcement in each AppStack (Phase 2: Detection)
Custom module force upgrade to later version of AppStack (phase 3: Remediation)
Module editor save to generate a PR instead of only saving locally
Inventory of Appstacks by each custom module by version(Phase 1: Visibility only) |  |  | arch
CLI version of chat agent

## Product Launch - Before Feb 202
Capability | Release month
Environment profiles public Beta | Feb
Cloud2Code (CLI) for Azure and AWS | Feb
Import custom TF modules from Git repo | Feb
manage your own TF module | Feb
UI enhancement - custom dropdown | Feb
Custom provider / custom resource support | Feb
IFC - C# analysis accuracy & stability improvement | Feb
UI improvement - json editor accepts string inputs | Feb
Bug fix - reduced page load time with resource icons | Feb
Bug fix - policy violation on topology page auto refreshes | Feb
5 more bug fixes | Feb

## Monthly launch process
Launch task | Frequency | Owner | Example |  | Training Meetings
problem requirements doc (PRD) | Major feature | Product | [PRD-May-Release] StackGen Compliance Dashboard | Use cases supported, maintenance
Design Figma | All | Product + design | compliance dashboard figma Alternative approach of crosslaunch Compliance Dashboard, Crossluanch 1, Crosslaunch 2, Crosslaunch 3 | First friday of month for PRD | First friday monthly
Scoping doc | Major feature | Engineering | Engineer scoping doc
ADR (if required) | Major feature | Engineering
Documentation | All | docs team | March release
Solution guide by Solution engineer | Major feature, integrations | SE | StackGen+Terraform Cloud guide (May) | screenshot walkthru', loom videos; align with marketing for external publishing; Marketing content calendar; prioritization framework for solutions guide - conference, top down
Technical demo to solutions engineer | semi monthly | Product + engineering | StackGen+Terraform Cloud guide (May)
Sales training / roadmap updates / playbook | Monthly | Product + Marketing | Product Roadmap: Rolling Four Quarters | align with marketing messaging | Monthly roadmap by PM. Partner with marketing on roadmap messaging
Messaging updates | TBD | Marketing |  |  | Marketing weekly thrice a week review with sales started by john@stackgen.com
Customer success | TBD | Customer Success

## Decks
2025-05-01
Quarterly Roadmap | Product Roadmap: Rolling Four Quarters
Competitive comparison | Competitive Comparison
Pricing calculator | StackGen pricing proposal - Apr 2025
2025-01-01
Competitive comparison | Competitive Comparison